## Test Summary
FARMAI MOBILE AUTOMATION EXECUTION SUMMARY
Project Name: | FARMAI Smart Farming Assistant
Testing Platform: | Android Mobile (Appium E2E)
Execution Date: | 13/6/2026
Environment: | Emulator / Android 13+ (Debug APK)
Metrics / Status | Test Count | Percentage | Status Remarks
Passed Tests | 48 | 94.1% | Fully verified features
Failed Tests | 3 | 5.9% | Requires engineering review
Skipped / Not Run | 0 | 0.0% | Not executed in this run
Total Scenarios | 51 | 100.0% | Full Appium E2E Automation Coverage
STATUS BREAKDOWN SUMMARY
🟢 PASS RATE: | 94.1%
🔴 FAIL RATE: | 5.9%
🟡 SKIPPED: | 0.0%

## Appium Test Cases
Test Case ID | Module | Test Scenario | Test Steps | Expected Result | Actual Result | Status | Date Verified | Remarks
APM-01 | Splash Screen | Verify App Logo display | 1. Launch FARMAI mobile app. 2. Observe splash interface. | App logo assets/images/logo.png renders clearly in center. | Logo displayed successfully. | PASS | 13/6/2026 | N/A
APM-02 | Splash Screen | Verify App Title branding | 1. Observe splash screen title text. | Branding text 'FARMAI' displays in bold dark green. | Title renders correctly. | PASS | 13/6/2026 | N/A
APM-03 | Splash Screen | Verify Tagline loading | 1. Check tagline text below the app title. | 'Smart Farming Assistant' tagline is visible. | Tagline text verified. | PASS | 13/6/2026 | N/A
APM-04 | Splash Screen | Verify Auto-Transition delay | 1. Wait on splash screen for 3 seconds. | Screen automatically redirects to Onboarding or Login. | Redirected to Onboarding screen. | PASS | 13/6/2026 | N/A
APM-05 | Onboarding Screen | Verify Onboarding slide details | 1. Transition to onboarding screen. 2. Verify background & title details. | Premium design cards with agricultural motifs load. | Design cards render correctly. | PASS | 13/6/2026 | N/A
APM-06 | Onboarding Screen | Verify Skip Button redirection | 1. Tap on the 'Skip' button on slide 1. | Instantly navigates to the Login screen. | Navigated to Login screen. | PASS | 13/6/2026 | N/A
APM-07 | Onboarding Screen | Verify Next Button clicks | 1. Tap 'Next' button on slide 1. 2. Observe transition to slide 2. | App swipingly transitions to slide 2 details. | Slide transitioned smoothly. | PASS | 13/6/2026 | N/A
APM-08 | Onboarding Screen | Verify Swipe Gesture navigation | 1. Swipe left across the screen. | Slide advances smoothly to the next card. | Swipe advances cards successfully. | PASS | 13/6/2026 | N/A
APM-09 | Onboarding Screen | Verify Get Started Button on last slide | 1. Navigate to final onboarding slide. 2. Tap 'Get Started'. | Navigates to Login Screen. | Navigated to Login. | PASS | 13/6/2026 | N/A
APM-10 | Login Screen | Verify form UI elements presence | 1. Open Login Screen. 2. Inspect input fields. | Email, Password inputs and 'Sign In' button are visible. | All fields are present. | PASS | 13/6/2026 | N/A
APM-11 | Login Screen | Verify password field masking | 1. Enter password 'secret123'. | Input characters are masked as dots for security. | Characters masked by default. | PASS | 13/6/2026 | N/A
APM-12 | Login Screen | Verify password visibility toggle | 1. Tap on the visibility eye icon. | Password characters reveal in clear text. | Text visible after toggle tap. | PASS | 13/6/2026 | N/A
APM-13 | Login Screen | Empty field submit validation | 1. Leave fields empty. 2. Tap 'Sign In'. | Validation triggers: 'Enter your email', 'Enter a password'. | Errors displayed under text fields. | PASS | 13/6/2026 | N/A
APM-14 | Login Screen | Invalid Email format check | 1. Enter 'invalidemail'. 2. Tap 'Sign In'. | Validation error: 'Enter a valid email address'. | Email error shown. | PASS | 13/6/2026 | N/A
APM-15 | Login Screen | Short password length check | 1. Enter '123'. 2. Tap 'Sign In'. | Validation error: 'Password must be at least 6 characters'. | Password error shown. | PASS | 13/6/2026 | N/A
APM-16 | Login Screen | Invalid credential rejection | 1. Enter 'wrong@email.com' and 'wrongpass'. 2. Tap 'Sign In'. | Alert Snack-bar shows: 'Invalid email or password'. | Alert popup displayed at bottom. | FAIL | 13/6/2026 | Failed because mock auth returned success instead of invalid rejection.
APM-17 | Login Screen | Navigate to Register page | 1. Tap 'Don\'t have an account? Register'. | App redirects to the Registration Screen. | Registration screen loaded. | PASS | 13/6/2026 | N/A
APM-18 | Login Screen | Successful Login execution | 1. Enter valid 'farmer@example.com' and 'password123'. 2. Tap 'Sign In'. | App logs in and redirects to the Dashboard/Home screen. | Successfully redirected to Home Dashboard. | PASS | 13/6/2026 | N/A
APM-19 | Register Screen | Verify form UI elements | 1. Open Register Screen. | Full Name, Email, Password, Confirm Password inputs are present. | All 4 inputs visible. | PASS | 13/6/2026 | N/A
APM-20 | Register Screen | Empty registration validate | 1. Keep all fields empty. 2. Tap 'Create Account'. | Validation errors shown for name, email, password. | Form validation rules fired. | PASS | 13/6/2026 | N/A
APM-21 | Register Screen | Password match validation | 1. Enter 'pass123' and 'pass456'. 2. Tap 'Create Account'. | Validation error: 'Passwords do not match'. | Error message displayed. | PASS | 13/6/2026 | N/A
APM-22 | Register Screen | Successful Registration mock | 1. Enter 'Ravi Kumar', 'new@email.com', 'password123', 'password123'. 2. Tap 'Create Account'. | Signs up successfully and navigates to the Dashboard. | Successfully signed up and loaded Dashboard. | PASS | 13/6/2026 | N/A
APM-23 | Register Screen | Back to Login link check | 1. Tap 'Already have an account? Login'. | Redirection goes back to the Login Screen. | Returned to Login. | PASS | 13/6/2026 | N/A
APM-24 | Register Screen | Validate Name field rules | 1. Enter only spaces in Full Name. 2. Tap Register. | Error: 'Enter your full name'. | Validation caught blank name. | PASS | 13/6/2026 | N/A
APM-25 | Dashboard | Validate screen load title | 1. Log in to dashboard. 2. Check header branding. | Displays 'FARMAI' logo and notification bells. | Branding elements rendered. | PASS | 13/6/2026 | N/A
APM-26 | Dashboard | Verify User Welcome name | 1. Read greeting text in header. | Shows 'Good morning, farmer' dynamically. | Displays 'farmer' extracted from email. | PASS | 13/6/2026 | N/A
APM-27 | Dashboard | Verify Weather Card status | 1. Inspect weather card loading. | Loads Salem APMC temperature (e.g. 32°C, Sunny). | Mock weather data loaded correctly. | PASS | 13/6/2026 | N/A
APM-28 | Dashboard | Verify Quick Actions grid | 1. Check four actions cards. | Cards: Disease Detection, Weather, Market, Irrigation exist. | All 4 cards loaded and responsive. | PASS | 13/6/2026 | N/A
APM-29 | Dashboard | Verify Market snapshot list | 1. Scroll to recent market prices. | Loads snapshot for Rice and Tomato with price levels. | Rice (₹2340) and Tomato (₹890) displayed. | PASS | 13/6/2026 | N/A
APM-30 | Dashboard | Verify Bottom Navigation items | 1. Observe bottom bar icons. | Contains Home, Forum, Helpline, and Profile links. | Navigation bar matches options. | PASS | 13/6/2026 | N/A
APM-31: Drawer | Dashboard | Verify Sidebar Navigation drawer | 1. Tap on drawer menu trigger. 2. Verify list options. | Drawer slideout contains Profile, Settings, History. | Sidebar list displays correctly. | PASS | 13/6/2026 | N/A
APM-32 | Crop Disease Prediction | Verify screen routing | 1. Tap 'Disease Detection' card. | Navigates to Disease Detection UI screen. | Disease Screen loaded. | PASS | 13/6/2026 | N/A
APM-33 | Crop Disease Prediction | Verify Image Upload option | 1. Tap on upload box container. | Presents dialog option: Camera or Gallery. | Image source selector modal opened. | PASS | 13/6/2026 | N/A
APM-34 | Crop Disease Prediction | Verify Analysis delay state | 1. Select image. 2. Tap 'Analyze Disease'. | Button shows Loading indicator, blocks interaction. | Loading spinner verifies busy state. | PASS | 13/6/2026 | N/A
APM-35 | Crop Disease Prediction | Verify Diagnosis outputs | 1. Wait for completion of analysis. | Displays result card: 'Leaf Blight (Xanthomonas oryzae)'. | Bacterial leaf blight result loaded. | PASS | 13/6/2026 | N/A
APM-36 | Crop Disease Prediction | Verify Treatment recommendations | 1. Scroll down disease result card. | Lists specific treatment suggestions like copper bactericides. | Recommendations are fully readable. | PASS | 13/6/2026 | N/A
APM-37 | Weather Alerts | Verify screen routing | 1. Tap 'Weather Alerts' card. | Navigates to full Weather Details page. | Weather Details page loaded. | PASS | 13/6/2026 | N/A
APM-38 | Weather Alerts | Verify temperature stats | 1. Inspect current temperature. | Shows Salem weather stats: 32° temperature. | Salem values verified. | PASS | 13/6/2026 | N/A
APM-39 | Weather Alerts | Verify 5-Day Forecast list scroll | 1. Scroll vertically through forecast lists. | Smooth vertical scrolling, displays daily forecast details. | Scrolling verified. | PASS | 13/6/2026 | N/A
APM-40 | Weather Alerts | Verify Farming Advisories | 1. Scroll to Farming Advisory card. | Renders advisory details containing seasonal action tips. | Advisory block rendered. | PASS | 13/6/2026 | N/A
APM-41 | Market Price Prediction | Verify crop detail filter tabs | 1. Navigate to Market page. 2. Tap 'Wheat' pill. | Prices update to display wheat trends. | Wheat prices and graph updated. | PASS | 13/6/2026 | N/A
APM-42 | Market Price Prediction | Verify price prediction graph | 1. Check price trend charts. | Graph renders curve representing actual vs predicted prices. | Interactive chart rendered. | PASS | 13/6/2026 | N/A
APM-43 | Market Price Prediction | Verify AI Market Advisory | 1. Check advisory advice card details. | Displays advisory text warning/advising about market movements. | Advisory tips loaded successfully. | PASS | 13/6/2026 | N/A
APM-44 | Smart Irrigation | Verify calculate water requirement | 1. Open Irrigation screen. 2. Select Rice, Loamy soil, 2 Acres. 3. Tap calculate. | Calculates correct recommended volume (e.g. 30m³). | Result shown on advice screen. | PASS | 13/6/2026 | N/A
APM-45 | Smart Irrigation | Verify history record save | 1. Complete calculation. 2. Check history records list. | New record added containing calculation inputs & date. | New item appears in list. | PASS | 13/6/2026 | N/A
APM-46 | Community Forum | Verify lists discussions list | 1. Navigate to Forum page. | Loads list of discussions cards with user avatars. | Forum list fully populated. | PASS | 13/6/2026 | N/A
APM-47 | Community Forum | Verify toggle like post | 1. Tap on heart icon on post 1. | Likes counter increments, color changes to red. | Like count toggled. | PASS | 13/6/2026 | N/A
APM-48 | Expert Support | Verify experts list online badge | 1. Navigate to Expert Helpline. 2. Tap 'Our Experts' tab. | List displays online/away badges on expert profile pics. | Experts online indicators rendered. | PASS | 13/6/2026 | N/A
APM-49 | Notifications | Verify listing items and badges | 1. Tap notification bell. | Opens notifications page showing reminders list. | Notifications items visible. | PASS | 13/6/2026 | N/A
APM-50 | Profile | Verify edit credentials validation | 1. Navigate to Profile. 2. Tap 'Edit', clear Full Name. 3. Tap 'Save'. | App displays profile update validation error. | Saving profile with blank name rejected. | FAIL | 13/6/2026 | Failed because blank name profile save bypassed validation and executed upload.
APM-51 | Profile | Verify logout confirmation dialog | 1. Tap 'Logout' menu tile. 2. Observe popup. | Displays AlertDialog: 'Are you sure you want to logout?'. | Confirmation dialog shown. | FAIL | 13/6/2026 | Dialog appeared but tapping logout button threw router exception.

## Pass Test Results
Test Case ID | Module | Test Scenario | Expected Result | Actual Result | Date Verified
APM-01 | Splash Screen | Verify App Logo display | App logo assets/images/logo.png renders clearly in center. | Logo displayed successfully. | 13/6/2026
APM-02 | Splash Screen | Verify App Title branding | Branding text 'FARMAI' displays in bold dark green. | Title renders correctly. | 13/6/2026
APM-03 | Splash Screen | Verify Tagline loading | 'Smart Farming Assistant' tagline is visible. | Tagline text verified. | 13/6/2026
APM-04 | Splash Screen | Verify Auto-Transition delay | Screen automatically redirects to Onboarding or Login. | Redirected to Onboarding screen. | 13/6/2026
APM-05 | Onboarding Screen | Verify Onboarding slide details | Premium design cards with agricultural motifs load. | Design cards render correctly. | 13/6/2026
APM-06 | Onboarding Screen | Verify Skip Button redirection | Instantly navigates to the Login screen. | Navigated to Login screen. | 13/6/2026
APM-07 | Onboarding Screen | Verify Next Button clicks | App swipingly transitions to slide 2 details. | Slide transitioned smoothly. | 13/6/2026
APM-08 | Onboarding Screen | Verify Swipe Gesture navigation | Slide advances smoothly to the next card. | Swipe advances cards successfully. | 13/6/2026
APM-09 | Onboarding Screen | Verify Get Started Button on last slide | Navigates to Login Screen. | Navigated to Login. | 13/6/2026
APM-10 | Login Screen | Verify form UI elements presence | Email, Password inputs and 'Sign In' button are visible. | All fields are present. | 13/6/2026
APM-11 | Login Screen | Verify password field masking | Input characters are masked as dots for security. | Characters masked by default. | 13/6/2026
APM-12 | Login Screen | Verify password visibility toggle | Password characters reveal in clear text. | Text visible after toggle tap. | 13/6/2026
APM-13 | Login Screen | Empty field submit validation | Validation triggers: 'Enter your email', 'Enter a password'. | Errors displayed under text fields. | 13/6/2026
APM-14 | Login Screen | Invalid Email format check | Validation error: 'Enter a valid email address'. | Email error shown. | 13/6/2026
APM-15 | Login Screen | Short password length check | Validation error: 'Password must be at least 6 characters'. | Password error shown. | 13/6/2026
APM-17 | Login Screen | Navigate to Register page | App redirects to the Registration Screen. | Registration screen loaded. | 13/6/2026
APM-18 | Login Screen | Successful Login execution | App logs in and redirects to the Dashboard/Home screen. | Successfully redirected to Home Dashboard. | 13/6/2026
APM-19 | Register Screen | Verify form UI elements | Full Name, Email, Password, Confirm Password inputs are present. | All 4 inputs visible. | 13/6/2026
APM-20 | Register Screen | Empty registration validate | Validation errors shown for name, email, password. | Form validation rules fired. | 13/6/2026
APM-21 | Register Screen | Password match validation | Validation error: 'Passwords do not match'. | Error message displayed. | 13/6/2026
APM-22 | Register Screen | Successful Registration mock | Signs up successfully and navigates to the Dashboard. | Successfully signed up and loaded Dashboard. | 13/6/2026
APM-23 | Register Screen | Back to Login link check | Redirection goes back to the Login Screen. | Returned to Login. | 13/6/2026
APM-24 | Register Screen | Validate Name field rules | Error: 'Enter your full name'. | Validation caught blank name. | 13/6/2026
APM-25 | Dashboard | Validate screen load title | Displays 'FARMAI' logo and notification bells. | Branding elements rendered. | 13/6/2026
APM-26 | Dashboard | Verify User Welcome name | Shows 'Good morning, farmer' dynamically. | Displays 'farmer' extracted from email. | 13/6/2026
APM-27 | Dashboard | Verify Weather Card status | Loads Salem APMC temperature (e.g. 32°C, Sunny). | Mock weather data loaded correctly. | 13/6/2026
APM-28 | Dashboard | Verify Quick Actions grid | Cards: Disease Detection, Weather, Market, Irrigation exist. | All 4 cards loaded and responsive. | 13/6/2026
APM-29 | Dashboard | Verify Market snapshot list | Loads snapshot for Rice and Tomato with price levels. | Rice (₹2340) and Tomato (₹890) displayed. | 13/6/2026
APM-30 | Dashboard | Verify Bottom Navigation items | Contains Home, Forum, Helpline, and Profile links. | Navigation bar matches options. | 13/6/2026
APM-31: Drawer | Dashboard | Verify Sidebar Navigation drawer | Drawer slideout contains Profile, Settings, History. | Sidebar list displays correctly. | 13/6/2026
APM-32 | Crop Disease Prediction | Verify screen routing | Navigates to Disease Detection UI screen. | Disease Screen loaded. | 13/6/2026
APM-33 | Crop Disease Prediction | Verify Image Upload option | Presents dialog option: Camera or Gallery. | Image source selector modal opened. | 13/6/2026
APM-34 | Crop Disease Prediction | Verify Analysis delay state | Button shows Loading indicator, blocks interaction. | Loading spinner verifies busy state. | 13/6/2026
APM-35 | Crop Disease Prediction | Verify Diagnosis outputs | Displays result card: 'Leaf Blight (Xanthomonas oryzae)'. | Bacterial leaf blight result loaded. | 13/6/2026
APM-36 | Crop Disease Prediction | Verify Treatment recommendations | Lists specific treatment suggestions like copper bactericides. | Recommendations are fully readable. | 13/6/2026
APM-37 | Weather Alerts | Verify screen routing | Navigates to full Weather Details page. | Weather Details page loaded. | 13/6/2026
APM-38 | Weather Alerts | Verify temperature stats | Shows Salem weather stats: 32° temperature. | Salem values verified. | 13/6/2026
APM-39 | Weather Alerts | Verify 5-Day Forecast list scroll | Smooth vertical scrolling, displays daily forecast details. | Scrolling verified. | 13/6/2026
APM-40 | Weather Alerts | Verify Farming Advisories | Renders advisory details containing seasonal action tips. | Advisory block rendered. | 13/6/2026
APM-41 | Market Price Prediction | Verify crop detail filter tabs | Prices update to display wheat trends. | Wheat prices and graph updated. | 13/6/2026
APM-42 | Market Price Prediction | Verify price prediction graph | Graph renders curve representing actual vs predicted prices. | Interactive chart rendered. | 13/6/2026
APM-43 | Market Price Prediction | Verify AI Market Advisory | Displays advisory text warning/advising about market movements. | Advisory tips loaded successfully. | 13/6/2026
APM-44 | Smart Irrigation | Verify calculate water requirement | Calculates correct recommended volume (e.g. 30m³). | Result shown on advice screen. | 13/6/2026
APM-45 | Smart Irrigation | Verify history record save | New record added containing calculation inputs & date. | New item appears in list. | 13/6/2026
APM-46 | Community Forum | Verify lists discussions list | Loads list of discussions cards with user avatars. | Forum list fully populated. | 13/6/2026
APM-47 | Community Forum | Verify toggle like post | Likes counter increments, color changes to red. | Like count toggled. | 13/6/2026
APM-48 | Expert Support | Verify experts list online badge | List displays online/away badges on expert profile pics. | Experts online indicators rendered. | 13/6/2026
APM-49 | Notifications | Verify listing items and badges | Opens notifications page showing reminders list. | Notifications items visible. | 13/6/2026

## Fail Test Results
Test Case ID | Module | Test Scenario | Expected Result | Actual Result | Remarks / Failure Reason | Date Verified
APM-16 | Login Screen | Invalid credential rejection | Alert Snack-bar shows: 'Invalid email or password'. | Alert popup displayed at bottom. | Failed because mock auth returned success instead of invalid rejection. | 13/6/2026
APM-50 | Profile | Verify edit credentials validation | App displays profile update validation error. | Saving profile with blank name rejected. | Failed because blank name profile save bypassed validation and executed upload. | 13/6/2026
APM-51 | Profile | Verify logout confirmation dialog | Displays AlertDialog: 'Are you sure you want to logout?'. | Confirmation dialog shown. | Dialog appeared but tapping logout button threw router exception. | 13/6/2026

## Bug Report
Bug ID | Associated TC ID | Module Name | Bug Title | Steps to Reproduce | Expected Behavior | Actual Behavior | Severity | Priority | Assigned To | Status
BUG-01 | APM-16 | Login Screen | Rejection alert snackbar fails to trigger on incorrect credentials | 1. Open Login Screen. 2. Input wrong@email.com and wrongpass. 3. Tap Sign In. | Show Snackbar warning 'Invalid email or password'. | Redirected to Dashboard with active mock session user profile. | High | High | Backend / Mobile Developer | Open
BUG-02 | APM-50 | Profile Screen | Full Name field updating updates empty username bypass validations | 1. Navigate to Profile. 2. Tap Edit. 3. Clear the Full Name input field. 4. Tap Save. | Prevent upload request and highlight input field with 'Name cannot be empty'. | Profile update calls executed successfully and sets database value to blank string. | Medium | Medium | Mobile UI Dev | Open
BUG-03 | APM-51 | Profile Screen | Logout confirmation buttons throws GoRouter navigation crash exception | 1. Navigate to Profile screen. 2. Scroll and tap Logout. 3. Tap 'Logout' button on AlertDialog. | Logs user out, clears Riverpod auth session states, and loads Login screen location. | App screens freeze and throw RouterException (No matching route found for /login). | High | High | Navigation / Router Team | Open